## Sheet1
Risk | Category | Probability | Impact | RE | Pointer to RMMM
Employees can be absent | Project Development | 50% | 3 | 100000 | Meet with the Employees to determine if they are healthy and are good in doing the project. But additional time in creating the project.
Corruption of Files | Project Development | 30% | 3 | 60000 | Always create a back up and make sure all computers are working fine. Check the computers and files if it's all good. Since we have a backup data we can restore them as fast as we can.
Cyber Attack | Project Development | 50% | 2 | 180000 | Maintain the Firewalls and Anti Virus to make sure that the hackers will have a hard time to get through. We can check the computers if they became slow without any reason, this could mean that there is a virus. Always make sure that all important files are secured and we have a department that can fix and solve the issue once it happened.
Workplace violence | Project Development | 10% | 4 | 10000
Workstation Crashed | Project Development | 60% | 4 | 15000 | Maintain that the computers are running fine and make sure that it can handle the various task that the programmers will be doing. Since we will create a back up we can just restore everything, and have the proper training to all employees regarding this issue.
Project didn't meet the deadline | Project Development | 80% | 2 | 300000 | Always maintain that the project is always on track every day. We will have a chart in weekly basis where the project should be. We will a lot more time and hire extra personnel to finish the job earlier.
No Internet Connection | Project Development | 70% | 2 | 100000 | We will make sure that the signal and connections are secured to avoid interruption. We will have a local IT team to monitor the internet connection. We won't rely on 1 service provider so that the project can continue without the other one.
In an Event of a Blackout | Project Development | 70% | 4 | 300000 | Always to make sure that the electric wires are in good shape and the location of the Project Development is not prone to blackouts. We can assume that this will happen if there are storms that are coming. We will have a backup Generator that can run so that the Project and the Computers won't crash and shutdown if ever this happens.
Risk of poorly designed App will likely lead to change of Interface problems later in project | Project Development | 80% | 3 | 250000 | Always make sure to ask user's, client and other people when creating the interface of the Program. If the Interface design is not what we expected the risk will likely to occur. We have people to monitor and can make changes in any given time that has the input of our clients and the users.
Risk of poorly program App will likely lead to bugs problems later in project | Project Development | 80% | 4 | 350000 | Always check that every programmer is aligned with each other and have an equal amount of time to test the program for bugs. It will highly occur when more people use the program and in quality testing. We will still have a head programmers that will check the programs and make sure that everything runs smoothly.